## 200413
Task | Category | Start Date | End Date
Descriptor/Property correlation | Initial data | 2020-04-13 | 2020-04-22
ML exploration (NN, RF, KRR) | Initial data | 2020-04-15 | 2020-04-29
Train models with data | Initial data | 2020-04-15 | 2020-04-29
Have model completed | Overall | 2020-06-05 | 2020-06-19

## 200422
Task | Category | Start Date | End Date
Descriptor/Property correlation | Initial data | 2020-04-13 | 2020-04-22
ML exploration (NN, RFR, KRR) | Initial data | 2020-04-15 | 2020-04-22
Train models with DFT data | Initial data | 2020-04-15 | 2020-04-22
Clean DFT data: outliers, normalize | Total data | 2020-04-22 | 2020-04-29
Descriptor importance: remove unecessary | Total data | 2020-04-24 | 2020-04-29
Train models with new DFT data (NN, RFR, LASSO, GPR) | Total data | 2020-04-24 | 2020-05-06
Test models with mixed alloy data | Total data | 2020-05-13 | 2020-05-20
Brainstorm more descriptors | Lit Review | 2020-05-15 | 2020-05-22
Expected improvement:informed selection of new training data | Bonus | 2020-05-20 | 2020-05-28
Have model completed | Overall | 2020-06-05 | 2020-06-19

## 200501
Task | Category | Start Date | End Date
Descriptor/Property correlation | Initial data | 2020-04-13 | 2020-04-22
ML exploration (NN, RFR, KRR) | Initial data | 2020-04-15 | 2020-04-22
Train models with DFT data | Initial data | 2020-04-15 | 2020-04-22
Clean DFT data: outliers, normalize | Total data | 2020-04-22 | 2020-04-29
Descriptor importance: remove unecessary | Total data | 2020-04-24 | 2020-04-29
Train models with new DFT data (NN, RFR, LASSO, GPR) | Total data | 2020-04-24 | 2020-05-06
Test models with mixed alloy data | Total data | 2020-05-13 | 2020-05-20
Data Visualization: PCA, KNN, MDS | Total data | 2020-04-29 | 2020-05-06
Expanded dataset (12k points) exploration | Chemical space | 2020-04-29 | 2020-05-13
Brainstorm more descriptors | Lit Review | 2020-05-15 | 2020-05-22
Expected improvement: informed selection of new training data | Bonus | 2020-05-20 | 2020-05-28
Have model completed | Overall | 2020-06-05 | 2020-06-19

## 200515
Task | Category | Start Date | End Date
Descriptor/Property correlation | Initial data | 2020-04-13 | 2020-04-22
ML exploration (NN, RFR, KRR) | Initial data | 2020-04-15 | 2020-04-22
Train models with DFT data | Initial data | 2020-04-15 | 2020-04-22
Clean DFT data: outliers, normalize | Total data | 2020-04-22 | 2020-04-29
Descriptor importance: remove unecessary | Total data | 2020-04-24 | 2020-04-29
Train models with new DFT data (NN, RFR, LASSO, GPR) | Total data | 2020-04-24 | 2020-05-06
Test models with mixed alloy data | Total data | 2020-05-22 | 2020-06-05
Data Visualization: PCA, KNN, MDS | Total data | 2020-04-29 | 2020-05-06
Outlier detection and removal: PCA, KNN | Total data | 2020-04-29 | 2020-05-06
Expanded dataset (12k points) exploration | Chemical space | 2020-04-29 | 2020-05-13
Outlier detection and removal | Chemical space | 2020-05-06 | 2020-05-13
Uncertainty prediction: all models | Chemical space | 2020-05-06 | 2020-05-20
Model tuning with new descriptors | New Total data | 2020-05-15 | 2020-05-27
Brainstorm more descriptors | Lit Review | 2020-05-15 | 2020-05-22
Expected improvement: informed selection of new training data | Bonus | 2020-05-20 | 2020-05-28
Have model completed | Overall | 2020-06-05 | 2020-06-19